## Slide 1
Reservation Migration Plan — Weekly Progress
Jun 1
Migration kickoff
Jun 8
LITE + SMB rollout
Jun 15
Accelerated migration
Jun 22
Mid-Market onboarding
Jun 29
Full segment coverage
Jul 6
GA readiness
Current Total
2,650
As of Jun 15
Week-over-Week
+141.6%
Jun 8 → Jun 15
Progress to Goal
31.2%
Target: 8,500
500
○
1,097
✓
2,650
✓
4,200
○
5,800
○
7,500
○
Guesty
○ Planned ✓ Actual

## Slide 2
Weekly Schedule Data (Editable)
Week | Label | Milestone | Total | LITE | SMB | Mid-Market | Status
Jun 1 | Week 1 | Migration kickoff | 500 | 200 | 300 | 0 | planned
Jun 8 | Week 2 | LITE + SMB rollout | 1097 | 380 | 717 | 0 | actual
Jun 15 | Week 3 | Accelerated migration | 2650 | 840 | 1810 | 0 | actual
Jun 22 | Week 4 | Mid-Market onboarding | 4200 | 1200 | 2500 | 500 | planned
Jun 29 | Week 5 | Full segment coverage | 5800 | 1600 | 3500 | 700 | planned
Jul 6 | Week 6 | GA readiness | 7500 | 2000 | 4500 | 1000 | planned
Edit the table above to update the chart. Final target: 8,500 accounts.