## Timeline
Guesty Program Timeline
Open API: 2026-07-01 → 2027-03-27 · Reservation Migration: Jun–Dec 2026
Program | Track | Milestone | Description | Date Label | Start Date | End Date | Status | Target Accounts | Actual Accounts | Variance
Account Migration | Weekly | Migration kickoff | Week 1 · Planned cumulative: 500 · Actual: 628 | Jun 1 | 2026-06-01 | 2026-06-01 | Actual | 500 | 628 | 128
Account Migration | Weekly | LITE + SMB rollout | Week 2 · Planned cumulative: 1,097 · Actual: 1,632 | Jun 8 | 2026-06-08 | 2026-06-08 | Actual | 1097 | 1632 | 535
Reservation Migration | Ramp-up | Ramp-up phase | 11,509 accounts · 7,090,000 reservations · 142,000 res/day | 6/15/2026 – 8/3/2026 | 2026-06-15 | 2026-08-03 | Planned | 11509
Account Migration | Weekly | Accelerated migration | Week 3 · Planned cumulative: 2,650 · Actual: 1,944 | Jun 15 | 2026-06-15 | 2026-06-15 | Actual | 2650 | 1944 | -706
Account Migration | Weekly | Mid-Market onboarding | Week 4 · Planned cumulative: 4,200 · Actual: 2,493 | Jun 22 | 2026-06-22 | 2026-06-22 | Actual | 4200 | 2493 | -1707
Account Migration | Status | Current cumulative (as of snapshot) | 2,493 accounts migrated | 6/22/2026 | 2026-06-22 | 2026-06-22 | Actual | 2493
Account Migration | Weekly | Full segment coverage | Week 5 · Planned cumulative: 5,800 | Jun 29 | 2026-06-29 | 2026-06-29 | Planned | 5800
Open API | New Users | Block API usage by registration date | By registration date, block API usage for new users | Early Q3 | 2026-07-01 | 2026-07-15 | Planned
Account Migration | Weekly | GA readiness | Week 6 · Planned cumulative: 7,500 | Jul 6 | 2026-07-06 | 2026-07-06 | Planned | 7500
Account Migration | Near-term | Near-term goal (8,500 accounts) | Target cumulative migrated accounts | 7/13/2026 | 2026-07-13 | 2026-07-13 | Planned | 8500
Reservation Migration | Steady Growth | Steady Growth phase | 8,513 accounts · 11,360,000 reservations · 227,200 res/day | 8/4/2026 – 9/22/2026 | 2026-08-04 | 2026-09-22 | Planned | 20022
Open API | Existing Users | Automated email to migrated users | Start sending automated email to migrated users | Beginning of Sept | 2026-09-01 | 2026-09-07 | Planned
Open API | Existing Users | Communication to all users | Sending communication to all users | End of September | 2026-09-22 | 2026-09-30 | Planned
Reservation Migration | Acceleration | Acceleration phase | 7,689 accounts · 15,640,000 reservations · 312,800 res/day | 9/23/2026 – 11/11/2026 | 2026-09-23 | 2026-11-11 | Planned | 27711
Reservation Migration | Full Speed | Full Speed phase | 7,290 accounts · 19,910,000 reservations · 398,200 res/day | 11/12/2026 – 12/31/2026 | 2026-11-12 | 2026-12-31 | Planned | 35001
Account Migration | Full Program | Full program (~35,001 accounts) | End of reservation migration program | 12/31/2026 | 2026-12-31 | 2026-12-31 | Planned | 35001
Open API | Existing Users | Deprecation of old Open API (OAPI) | End of deprecation period for old OAPI | EO March 27 | 2027-03-27 | 2027-03-27 | Planned
Gantt Data (for chart below)
Milestone | Start Date | End Date | Duration (days)
Ramp-up phase | 2026-06-15 | 2026-08-03 | 50
Steady Growth phase | 2026-08-04 | 2026-09-22 | 50
Acceleration phase | 2026-09-23 | 2026-11-11 | 50
Full Speed phase | 2026-11-12 | 2026-12-31 | 50
Block API usage by registration date | 2026-07-01 | 2026-07-15 | 1
Automated email to migrated users | 2026-09-01 | 2026-09-07 | 1
Communication to all users | 2026-09-22 | 2026-09-30 | 1
Deprecation of old Open API (OAPI) | 2027-03-27 | 2027-03-27 | 1
Import to Google Sheets: Upload this file to Google Drive → Open with Google Sheets. Or use File → Import → Upload in sheets.google.com.

## Open API
Track | Date Label | Start | End | Milestone | Description
New Users | Early Q3 | 2026-07-01 | 2026-07-15 | Block API usage by registration date | By registration date, block API usage for new users
Existing Users | Beginning of Sept | 2026-09-01 | 2026-09-07 | Automated email to migrated users | Start sending automated email to migrated users
Existing Users | End of September | 2026-09-22 | 2026-09-30 | Communication to all users | Sending communication to all users
Existing Users | EO March 27 | 2027-03-27 | 2027-03-27 | Deprecation of old Open API (OAPI) | End of deprecation period for old OAPI

## Weekly Migration
Week | Milestone | Status | Planned Cumulative | Actual Cumulative | Variance | Weekly Lite | Weekly Pro | Weekly Enterprise | Weekly Total
4/13/2026 |  | Actual |  | 5 |  | 5 | 0 | 0 | 5
4/20/2026 |  | Actual |  | 20 |  | 11 | 4 | 0 | 15
4/27/2026 |  | Actual |  | 59 |  | 28 | 11 | 0 | 39
5/4/2026 |  | Actual |  | 68 |  | 6 | 3 | 0 | 9
5/11/2026 |  | Actual |  | 87 |  | 11 | 8 | 0 | 19
5/18/2026 |  | Actual |  | 126 |  | 23 | 16 | 0 | 39
5/25/2026 |  | Actual |  | 383 |  | 159 | 98 | 0 | 257
6/1/2026 | Migration kickoff | Actual | 500 | 628 | 128 | 109 | 136 | 0 | 245
6/8/2026 | LITE + SMB rollout | Actual | 1097 | 1632 | 535 | 424 | 571 | 9 | 1004
6/15/2026 | Accelerated migration | Actual | 2650 | 1944 | -706 | 0 | 312 | 0 | 312
6/22/2026 | Mid-Market onboarding | Actual | 4200 | 2493 | -1707 | 3 | 546 | 0 | 549
6/29/2026 | Full segment coverage | Planned | 5800
7/6/2026 | GA readiness | Planned | 7500

## Reservation Phases
Phase | Start | End | Days | Accounts | Reservations | Res/Day | Res/Account
Ramp-up | 6/15/2026 | 8/3/2026 | 50 | 11509 | 7090000 | 142000 | 616
Steady Growth | 8/4/2026 | 9/22/2026 | 50 | 8513 | 11360000 | 227200 | 1335
Acceleration | 9/23/2026 | 11/11/2026 | 50 | 7689 | 15640000 | 312800 | 2034
Full Speed | 11/12/2026 | 12/31/2026 | 50 | 7290 | 19910000 | 398200 | 2731