## Slide 1
Open API — Milestone Timeline
Jul 2026 → Mar 2027 · Click any text to edit after import
Jun 2026
Mar 2027
Jan 2027
New Users
Early Q3
Block API usage by registration date
Existing Users
Beginning of Sept
Automated email to migrated users
End of September
Communication to all users
EO March 27
Deprecation of old Open API (OAPI)
New Users
Early Q3 — Block API by registration date
Existing Users
Sept emails → Sept comms → Mar 27 OAPI deprecation
Guesty

## Slide 2
Reservation Migration — Phase Timeline
Jun 15 – Dec 31, 2026 · ~35K accounts · ~54M reservations
Jun 2026
Mar 2027
Jan 2027
Ramp-up
11,509 accts
11,509 accounts · 7,090,000 reservations · 142,000 res/day
Steady Growth
20,022 accts
8,513 accounts · 11,360,000 reservations · 227,200 res/day
Acceleration
27,711 accts
7,689 accounts · 15,640,000 reservations · 312,800 res/day
Full Speed
35,001 accts
7,290 accounts · 19,910,000 reservations · 398,200 res/day
Guesty

## Slide 3
Full Program Timeline — Data (Editable)
Edit cells below, then update the visual slides to match.
Program | Track | Date | Milestone | Description | Status
Account Migration | Weekly | Jun 1 | Migration kickoff | Week 1 · Planned cumulative: 500 · Actual: 628 | Actual
Account Migration | Weekly | Jun 8 | LITE + SMB rollout | Week 2 · Planned cumulative: 1,097 · Actual: 1,632 | Actual
Reservation Migration | Ramp-up | 6/15/2026 – 8/3/2026 | Ramp-up phase | 11,509 accounts · 7,090,000 reservations · 142,000 res/day | Planned
Account Migration | Weekly | Jun 15 | Accelerated migration | Week 3 · Planned cumulative: 2,650 · Actual: 1,944 | Actual
Account Migration | Weekly | Jun 22 | Mid-Market onboarding | Week 4 · Planned cumulative: 4,200 · Actual: 2,493 | Actual
Account Migration | Status | 6/22/2026 | Current cumulative (as of snapshot) | 2,493 accounts migrated | Actual
Account Migration | Weekly | Jun 29 | Full segment coverage | Week 5 · Planned cumulative: 5,800 | Planned
Open API | New Users | Early Q3 | Block API usage by registration date | By registration date, block API usage for new users | Planned
Account Migration | Weekly | Jul 6 | GA readiness | Week 6 · Planned cumulative: 7,500 | Planned
Account Migration | Near-term | 7/13/2026 | Near-term goal (8,500 accounts) | Target cumulative migrated accounts | Planned
Reservation Migration | Steady Growth | 8/4/2026 – 9/22/2026 | Steady Growth phase | 8,513 accounts · 11,360,000 reservations · 227,200 res/day | Planned
Open API | Existing Users | Beginning of Sept | Automated email to migrated users | Start sending automated email to migrated users | Planned
Open API | Existing Users | End of September | Communication to all users | Sending communication to all users | Planned
Reservation Migration | Acceleration | 9/23/2026 – 11/11/2026 | Acceleration phase | 7,689 accounts · 15,640,000 reservations · 312,800 res/day | Planned
Reservation Migration | Full Speed | 11/12/2026 – 12/31/2026 | Full Speed phase | 7,290 accounts · 19,910,000 reservations · 398,200 res/day | Planned
Account Migration | Full Program | 12/31/2026 | Full program (~35,001 accounts) | End of reservation migration program | Planned
Open API | Existing Users | EO March 27 | Deprecation of old Open API (OAPI) | End of deprecation period for old OAPI | Planned