## Data
Week Starting | Weekly Actual | Cumulative Actual | Planned Cumulative | Variance (Actual - Planned)
4/13/2026 | 5 | 5
4/20/2026 | 15 | 20
4/27/2026 | 39 | 59
5/4/2026 | 9 | 68
5/11/2026 | 19 | 87
5/18/2026 | 39 | 126
5/25/2026 | 257 | 383
6/1/2026 | 245 | 628 | 500 | 128
6/8/2026 | 1004 | 1632 | 1097 | 535
6/15/2026 | 1944 | 3576 | 2650 | 926
6/22/2026 |  |  | 4200
6/29/2026 |  |  | 5800
7/6/2026 |  |  | 7500

## Weekly Detail
Week Starting | Lite | Pro | Enterprise | Weekly Total
4/13/2026 | 5 | 0 | 0 | 5
4/20/2026 | 11 | 4 | 0 | 15
4/27/2026 | 28 | 11 | 0 | 39
5/4/2026 | 6 | 3 | 0 | 9
5/11/2026 | 11 | 8 | 0 | 19
5/18/2026 | 23 | 16 | 0 | 39
5/25/2026 | 159 | 98 | 0 | 257
6/1/2026 | 109 | 136 | 0 | 245
6/8/2026 | 424 | 571 | 9 | 1004
6/15/2026 | 776 | 1159 | 9 | 1944

## Migration Phases
Phase | Start | End | Days | Avg Res/Day | Total Reservations | Accounts (Phase) | Avg Res/Account | Processing @ 900/min | Processing @ 8,024/min | Processing @ 14,000/min
Ramp-up | 6/15/2026 | 8/3/2026 | 50 | 142000 | 7090000 | 11509 | 616 | 2h 38m | 18m | 10m
Steady Growth | 8/4/2026 | 9/22/2026 | 50 | 227200 | 11360000 | 8513 | 1335 | 4h 12m | 28m | 16m
Acceleration | 9/23/2026 | 11/11/2026 | 50 | 312800 | 15640000 | 7689 | 2034 | 5h 48m | 39m | 22m
Full Speed | 11/12/2026 | 12/31/2026 | 50 | 398200 | 19910000 | 7290 | 2731 | 7h 22m | 50m | 28m
TOTAL |  |  | 200 |  | 54000000 | 35001

## Phase Timeline
Phase | End Date | Accounts This Phase | Cumulative Accounts
Ramp-up | 8/3/2026 | 11509 | 11509
Steady Growth | 9/22/2026 | 8513 | 20022
Acceleration | 11/11/2026 | 7689 | 27711
Full Speed | 12/31/2026 | 7290 | 35001
Current status (as of 6/15/2026) | 6/15/2026 |  | 3576
Recent run rate (accounts/day) |  |  | 277.7

## Projections
Goal | Target | Scenario | Accounts/Day | Days Remaining | Projected Finish | Planned Finish | Days Ahead of Plan
Near-term goal (8,500 accounts) | 8500 | Current pace | 277.7 | 17.7 | 07/02/2026 | 7/13/2026 | 10
Near-term goal (8,500 accounts) | 8500 | Ramp-up phase pace | 230.2 | 21.4 | 07/06/2026 | 7/13/2026 | 6
Near-term goal (8,500 accounts) | 8500 | Near-term plan pace | 158.8 | 31 | 07/16/2026 | 7/13/2026 | -3
End of Ramp-up (11,509 accounts) | 11509 | Current pace | 277.7 | 28.6 | 07/13/2026 | 8/3/2026 | 20
End of Ramp-up (11,509 accounts) | 11509 | Ramp-up phase pace | 230.2 | 34.5 | 07/19/2026 | 8/3/2026 | 14
End of Ramp-up (11,509 accounts) | 11509 | Near-term plan pace | 158.8 | 49.9 | 08/03/2026 | 8/3/2026 | -1
Full program (~35,001 accounts) | 35001 | Current pace | 277.7 | 113.2 | 10/06/2026 | 12/31/2026 | 85
Full program (~35,001 accounts) | 35001 | Ramp-up phase pace | 230.2 | 136.5 | 10/29/2026 | 12/31/2026 | 62
Full program (~35,001 accounts) | 35001 | Near-term plan pace | 158.8 | 197.8 | 12/29/2026 | 12/31/2026 | 1
Days Ahead of Plan = positive means finishing BEFORE planned date. Based on 3,576 accounts as of 6/15/2026.
Note: Full program projection assumes constant account pace. Later phases (Steady Growth → Full Speed) require 2–4× more reservations per account; reservation throughput (900 vs 8,024 vs 14,000/min) may constrain finish date even if account onboarding stays ahead.

## Chart
To use in Google Sheets: Upload to Google Drive → Open with Google Sheets. Edit Data / Migration Phases / Projections tabs. Tabs: Data, Weekly Detail, Migration Phases, Phase Timeline, Projections, Chart.